## Sheet1
Release | Week | User Story | Description | Priority | Time(days) | Time(days) w Vel 70% | Status
Alpha ICT 2 | 1 | Homepage | Homepage with new theme and upgraded logo. Product's pictures has been added into slider. | 10 | 7 | 10 | done
| 2 | Wishlist | User can add their favourite items into wish list for future purchase. | 10 | 7 | 10 | done
| 3 | Shop | Few products has been added into shop page from where user can put items into shopping cart. | 5 | 7 | 10 | done
|  |  | sum |  | 21 | 30
Beta ICT 2 | 4 | My Account | User can log into his account if he has registered with website. | 10 | 7 | 10 | done
| 5 | About | All the information about the store has been updated into this page. | 10 | 7 | 10 | done
| 6 | Shopping Cart | Content management, quantity and price of product can be seen in this section. | 5 | 7 | 10 | done
|  |  | sum |  | 21 | 30
Final ICT 2 | 7 | Checkout & Payment | This section will display the biling details and payment method which will be paypal. | 10 | 7 | 10 | in progress
| 7 | SEO | Using keyword Reliance fresh for homepage. | 5 | 7 | 10 | in progress
| 8 | Google Analytics | for tracking the user who visit the website with location. | 5 | 7 | 10 | in progress
| 9 | Social Media Live feeds | this site will be linked to facebook account. | 5 | 7 | 10 | in progress
| 10 | Bug Fixes | any updation will be done as per client's advice. | 10 | 7 | 10 | in progress
|  |  | sum |  | 35 | 50

## Sheet1 (2)
Release | Week | User Story | Description | Priority | Test by Client | Status
Alpha ICT 2 | 1 | Homepage | Homepage with new theme and upgraded logo. Product's pictures has been added into slider. | 10 | Yes | Approved
| 2 | Wishlist | User can add their favourite items into wish list for future purchase. | 10 | Yes | Approved
| 3 | Shop | Few products has been added into shop page from where user can put items into shopping cart. | 5 | Yes | Approved
Beta ICT 2 | 4 | My Account | User can log into his account if he has registered with website. | 10 | Yes | Approved
| 5 | About | All the information about the store has been updated into this page. | 10 | Yes | Approved
| 6 | Shopping Cart | Content management, quantity and price of product can be seen in this section. | 5 | Yes | Approved
Final ICT 2 | 7 | Checkout & Payment | This section will display the biling details and payment method which will be paypal. | 10 |  | in progress
| 7 | SEO | Using keyword Reliance fresh for homepage. | 5 |  | in progress
| 8 | Google Analytics | for tracking the user who visit the website with location. | 5 |  | in progress
| 9 | Social Media Live feeds | this site will be linked to facebook account. | 5 |  | in progress
| 10 | Bug Fixes | any updation will be done as per client's advice. | 10 |  | in progress