## Trang_tính1
User Stories | Start | Week 5 (in days) | Week4 (in days) | Week3 (in days) | Week2 (in days) | Week1 (in days) | Total
HomePage | 10 | 2 | 3 | 2 | 1 | 2 | 10
Shopping cart | 10 | 1 | 3 | 2 | 3 | 1 | 10
Wish List | 10 | 0 | 4 | 2 | 1 | 3 | 10
Shop | 10 | 1 | 2 | 3 | 4 | 0 | 10
Time | Start | Week5 (in days) | Week4 (in days) | Week3 (in days) | Week2 (in days) | Week1 (in days) | Total
Actual remaining (Days) | 40 | 36 | 24 | 15 | 6 | 0 | 81
Estimated remaining (Days) | 40 | 32 | 24 | 16 | 8 | 0 | 80